## Sheet2
Row Labels | Count of ID
DONE | 2
IN PROGRESS | 1
OPEN | 11
Grand Total | 14

## Sheet1
ID | Page | Issue | Priority | Status | Obs
1 | Report Incident | Get address location from the map - currently, it is only possible to get the location by typing it. | HIGH | cancelled
2 | Report Incident | Format adress form - fields layout is inconsistent | LOW | cancelled
3 | Report Incident | Format submit button - is taking all the width | LOW | cancelled
4 | Login and Register | Add header menu | MEDIUM | OPEN
5 | View Incidents | Will be home page | HIGH | DONE | yes, the incidents will be shown on the main page
6 | View Incidents | Plot incidents on map | HIGH | DONE
7 | Report Incident | Upload photo - enable photo upload | HIGH | DONE
8 | View Incidents Trend | Create page | LOW | OPEN
9 | Register User | Validate if email is unique | MEDIUM | OPEN
10 | Report Incident | change text from "car crash" to "car accident", to be more ample? | LOW | OPEN
11 | IncidentApp | Add general /error page | LOW | OPEN
12 | Main page | Add pop up in incident icon showing the incident details | HIGH | DONE
13 | Main page | Add pop up in current location showing total and total by incident type on that area on the map | HIGH | OPEN
14 | Main page | Add new incident on a incident marker using pop up window | HIGH | IN PROGRESS
15 | Report Incident | Bug - creating permanent markers as addresses are being searched | LOW | OPEN
16 | Report Incident | Bug- when reporting new incident, all other incidents infowindows change to the same photo and information | HIGH | OPEN
17 | Report Incident | When reporting new incident +2 infowindows open they don't close | MEDIUM | OPEN